Project Timeline

Towards Semantically-Aware End-of-Utterance Detection

Revised plan · 9 weeks (7 Jul – 4 Sep) · 2 hard deadlines · github.com/jean-baptisteAZAN/EOUDetector

| Wk | Dates | Focus & deliverables |
| --- | --- | --- |
| 1 | 7–13 Jul | Data foundation • Build & run the dataset generator over the ~4k transcripts: prefix-truncation labelling, Azure-style normalisation (lowercase, no punctuation, keep disfluencies), hard-case augmentation (spelling, numbers, dates, posology), class balancing. • Secure a small labelled AUDIO clip set (~50–100 clips, hand-labelled), required for acoustic & end-to-end evaluation. • Kick off the literature review (runs continuously from here). Eval metrics already scaffolded. |
| 2 | 14–20 Jul | Lexical model • Fine-tune CamemBERT on the real dataset → usable lexical EOU model. Verify it actually learns (loss curves, no class collapse), pick best checkpoint, export to ONNX, wrap behind LexicalEOU. • Establish the semantic-only baseline on a held-out test set. Continue lit review. |
| 3 | 21–27 Jul | Pipeline modules • Implement/finish the decoupled modules (Silero VAD, Azure ASR + recognizing partials, Smart Turn v3 acoustic, lexical wrapper + FR heuristic veto, endpoint controller) and the orchestrator. • Baselines: VAD-only (silence-timeout) and Smart-Turn-only (acoustic). Start drafting the Methodology section. |
| 4 | 28 Jul–3 Aug | End-to-end system • Wire the full real-time pipeline with rule-based bilateral-veto fusion + dynamic endpoint; finish the demo (mic/wav) and eval harness; produce first whole-system numbers on the labelled clips. Continue Methodology draft. |
| 5 | 4–10 Aug | Learned fusion (stretch, data-gated) • If enough aligned audio+text+label examples exist: train a logistic fusion on [p_ac, p_lex] and compare against rule-based. If not: tune/robustify rule-based thresholds and deepen error analysis instead. • Rule-based fusion remains the guaranteed deliverable. ½-week slack. |
| 6 | 11–17 Aug | Evaluation • Full evaluation + ablations (VAD-only → +acoustic → +lexical → full fusion) + error analysis on the three false-positive classes (spelling, chunked numbers/dates, thinking pauses). • Freeze results. Draft the Results section from the numbers. |
| 7 | 18–21 Aug | Corpus submission • Finalise & package the code corpus, reproducible (README, pinned deps, run/eval scripts), PHI-free (no transcripts / audio / keys). Consolidate the already-drafted methodology & results. Buffer. • → Corpus submission, Fri 21 Aug. |
| 8 | 25–31 Aug | Write-up • Complete the dissertation draft (evaluation, discussion, conclusions, future work); record the demo video; compile the logbook. Full internal read-through. |
| 9 | 1–4 Sep | Final polish • Abstract, proofreading, formatting, contingency buffer. • → Submit dissertation + abstract + video + logbook, Fri 4 Sep. |

Milestones

Fri 21 Aug, code corpus submission (reproducible, PHI-free).

Fri 4 Sep, dissertation + abstract + video + logbook.

Continuous workstreams (not one-off weeks)

Literature review, continuous W1 → W6.

Writing, incremental: Methodology W3–4, Results W6, full draft W8 (deliberately not back-loaded into the final fortnight).

Version control, PHI-safe throughout: data, audio and keys git-ignored; notebook outputs cleared before commit.

Key changes vs. the original timeline (points challenged)

Added the missing labelled AUDIO dataset. The original only planned the text dataset, but Smart Turn evaluation, end-to-end evaluation and learned fusion all need labelled audio, otherwise those steps have nothing to run on.

Literature review moved to W1 (was W4) and made continuous, starting it at W4 risks a thin related-work section.

Writing made incremental from W3 (was concentrated in W7–9), back-loading all writing into the final two weeks costs dissertation quality.

Learned fusion re-scoped as a data-gated stretch goal; rule-based bilateral-veto fusion is the guaranteed core deliverable (it needs no training).

Added explicit slack before both hard deadlines (½-week in W5, buffers in W7 and W9), the original had zero margin against two fixed dates.

W1 data step made explicit about quality (normalisation, hard-case coverage, class balancing) after the observed CamemBERT collapse on toy data (loss ≈ ln 2, predicted one class for all).

Key risks & mitigations

Labelled audio is scarce → start small / hand-labelled in W1; expand annotation later if needed (phase 2).

Model collapse / weak lexical signal → data-quality checks + FR heuristic veto as a deterministic safety net in front of the model.

Learned fusion lacks aligned data → keep rule-based fusion primary; treat learned fusion as stretch.

Deadline slippage → incremental writing + explicit buffers (W5/W7/W9).

PHI leak in repo or notebook outputs → .gitignore for data/audio/keys; clear notebook outputs before every commit.

Dependencies to watch

W2 (fine-tune) depends 100% on W1 (data), front-load data; a W1 slip cascades through the whole plan.

W3 Smart-Turn-only baseline and the W4 eval harness both depend on the W1 audio clip set.